## ecommerce
Ecommerce
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
Start
Name | Owner | Status | Timeline - Start | Timeline - End | Dependent On
Selecting the project | Anas Syed, Jayanth K, Deleted on invitation cancelation, anji | Done | 2025-03-15 | 2025-03-16
Requirment analysis | Anas Syed, Deleted member, Jayanth K, Fayaz, Deleted on invitation cancelation, anji | Done | 2025-03-16 | 2025-03-20 | Selecting the project
Assigning task | Anas Syed | Done | 2025-03-19 | 2025-03-20 | Requirment analysis
|  |  | 2025-03-15 | 2025-03-20
UI/Ux design
Name | Owner | Status | Timeline - Start | Timeline - End | Dependent On
Add login page/ sign up page | Deleted member, anji | Done | 2025-03-21 | 2025-03-27 | Requirment analysis
Product list page | Deleted member, anji | Done | 2025-03-21 | 2025-03-27 | Requirment analysis
Product development page | Deleted member, anji | Done | 2025-03-21 | 2025-03-27 | Requirment analysis
Cart page | Deleted member, anji | Done | 2025-03-21 | 2025-03-27 | Requirment analysis
Payment gateway | Deleted member, anji | Working on it | 2025-03-21 | 2025-03-27 | Requirment analysis
|  |  | 2025-03-21 | 2025-03-27
Backend development
Name | Owner | Status | Timeline - Start | Timeline - End | Dependent On
Low level design | Fayaz, Deleted on invitation cancelation | Not Started | 2025-03-27 | 2025-04-14 | Requirment analysis
API for plp,pdp,signup,login | Fayaz, Deleted on invitation cancelation | Not Started | 2025-03-24 | 2025-04-11 | Low level design
Inventory management system | Fayaz, Deleted on invitation cancelation | Not Started | 2025-03-27 | 2025-04-14 | API for plp,pdp,signup,login
Customer Management system | Fayaz, Deleted on invitation cancelation | Not Started | 2025-03-27 | 2025-04-14 | API for plp,pdp,signup,login
order management system | Fayaz, Deleted on invitation cancelation | Not Started | 2025-03-27 | 2025-04-14 | API for plp,pdp,signup,login
|  |  | 2025-03-24 | 2025-04-14
Database setup
Name | Owner | Status | Timeline - Start | Timeline - End | Dependent On
RDS setup | Anas Syed, Jayanth K | Not Started | 2025-04-14 | 2025-04-17 | Requirment analysis
|  |  | 2025-04-14 | 2025-04-17
Infrastructure Setup
Name | Owner | Status | Timeline - Start | Timeline - End | Dependent On
Setting up EC2 machines | Anas Syed, Deleted on invitation cancelation | Not Started | 2025-04-17 | 2025-04-21 | RDS setup
setting up docker services | Fayaz, Deleted on invitation cancelation | Not Started | 2025-04-17 | 2025-04-21 | Setting up EC2 machines
Setting up load balancer | Deleted on invitation cancelation, Anas Syed | Not Started | 2025-04-17 | 2025-04-21 | setting up docker services
configuring routing | Deleted on invitation cancelation, Fayaz | Not Started | 2025-04-17 | 2025-04-21 | setting up docker services
source code management | Deleted on invitation cancelation, Anas Syed | Not Started | 2025-04-17 | 2025-04-21 | Requirment analysis
|  |  | 2025-04-17 | 2025-04-21
Merging microservices
Name | Owner | Status | Timeline - Start | Timeline - End | Dependent On
Merging microservices | Anas Syed, Fayaz, Jayanth K | Not Started | 2025-04-21 | 2025-04-23 | source code management
|  |  | 2025-04-21 | 2025-04-23
Testing and QA
Name | Owner | Status | Timeline - Start | Timeline - End | Dependent On
Manual testing | anji, Deleted member | Not Started | 2025-04-23 | 2025-04-26 | Merging microservices
Unit testing | anji, Deleted member | Not Started | 2025-04-23 | 2025-04-26 | Merging microservices
|  |  | 2025-04-23 | 2025-04-26
Deployment
Name | Owner | Status | Timeline - Start | Timeline - End | Dependent On
Final Deployment | Anas Syed, Fayaz | Not Started | 2025-04-26 | 2025-04-27 | Unit testing
|  |  | 2025-04-26 | 2025-04-27