## Gantt
Board - Ecommerce (by months)
|  |  | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | May-2025 | May-2025 | May-2025 | May-2025 | Jun-2025 | Jun-2025 | Jun-2025 | Jun-2025 | Jun-2025 | Jul-2025 | Jul-2025 | Jul-2025 | Jul-2025 | Aug-2025 | Aug-2025 | Aug-2025 | Aug-2025 | Sep-2025 | Sep-2025 | Sep-2025 | Sep-2025 | Sep-2025 | Oct-2025 | Oct-2025
| Start | End | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13
Requirment analysis | 16-Mar-2025 | 20-Mar-2025 | 10: Requirment analysis (16-Mar-25 - 20-Mar-25); 17: Requirment analysis (16-Mar-25 - 20-Mar-25)
Assigning task | 19-Mar-2025 | 20-Mar-2025 | 17: Assigning task (19-Mar-25 - 20-Mar-25)
Add login page/ sign up page | 21-Mar-2025 | 27-Mar-2025 | 17: Add login page/ sign up page (21-Mar-25 - 27-Mar-25); 24: Add login page/ sign up page (21-Mar-25 - 27-Mar-25)
Product list page | 21-Mar-2025 | 27-Mar-2025 | 17: Product list page (21-Mar-25 - 27-Mar-25); 24: Product list page (21-Mar-25 - 27-Mar-25)
Product development page | 21-Mar-2025 | 27-Mar-2025 | 17: Product development page (21-Mar-25 - 27-Mar-25); 24: Product development page (21-Mar-25 - 27-Mar-25)
Cart page | 21-Mar-2025 | 27-Mar-2025 | 17: Cart page (21-Mar-25 - 27-Mar-25); 24: Cart page (21-Mar-25 - 27-Mar-25)
Payment gateway | 21-Mar-2025 | 27-Mar-2025 | 17: Payment gateway (21-Mar-25 - 27-Mar-25); 24: Payment gateway (21-Mar-25 - 27-Mar-25)
API for plp,pdp,signup,login | 24-Mar-2025 | 11-Apr-2025 | 24: API for plp,pdp,signup,login (24-Mar-25 - 11-Apr-25); 31: API for plp,pdp,signup,login (24-Mar-25 - 11-Apr-25); 7: API for plp,pdp,signup,login (24-Mar-25 - 11-Apr-25)
Low level design | 27-Mar-2025 | 14-Apr-2025 | 24: Low level design (27-Mar-25 - 14-Apr-25); 31: Low level design (27-Mar-25 - 14-Apr-25); 7: Low level design (27-Mar-25 - 14-Apr-25); 14: Low level design (27-Mar-25 - 14-Apr-25)
Inventory management system | 27-Mar-2025 | 14-Apr-2025 | 24: Inventory management system (27-Mar-25 - 14-Apr-25); 31: Inventory management system (27-Mar-25 - 14-Apr-25); 7: Inventory management system (27-Mar-25 - 14-Apr-25); 14: Inventory management system (27-Mar-25 - 14-Apr-25)
Customer Management system | 27-Mar-2025 | 14-Apr-2025 | 24: Customer Management system (27-Mar-25 - 14-Apr-25); 31: Customer Management system (27-Mar-25 - 14-Apr-25); 7: Customer Management system (27-Mar-25 - 14-Apr-25); 14: Customer Management system (27-Mar-25 - 14-Apr-25)
order management system | 27-Mar-2025 | 14-Apr-2025 | 24: order management system (27-Mar-25 - 14-Apr-25); 31: order management system (27-Mar-25 - 14-Apr-25); 7: order management system (27-Mar-25 - 14-Apr-25); 14: order management system (27-Mar-25 - 14-Apr-25)
RDS setup | 14-Apr-2025 | 17-Apr-2025 | 14: RDS setup (14-Apr-25 - 17-Apr-25)
Setting up EC2 machines | 17-Apr-2025 | 21-Apr-2025 | 14: Setting up EC2 machines (17-Apr-25 - 21-Apr-25); 21: Setting up EC2 machines (17-Apr-25 - 21-Apr-25)
setting up docker services | 17-Apr-2025 | 21-Apr-2025 | 14: setting up docker services (17-Apr-25 - 21-Apr-25); 21: setting up docker services (17-Apr-25 - 21-Apr-25)
Setting up load balancer | 17-Apr-2025 | 21-Apr-2025 | 14: Setting up load balancer (17-Apr-25 - 21-Apr-25); 21: Setting up load balancer (17-Apr-25 - 21-Apr-25)
configuring routing | 17-Apr-2025 | 21-Apr-2025 | 14: configuring routing (17-Apr-25 - 21-Apr-25); 21: configuring routing (17-Apr-25 - 21-Apr-25)
source code management | 17-Apr-2025 | 21-Apr-2025 | 14: source code management (17-Apr-25 - 21-Apr-25); 21: source code management (17-Apr-25 - 21-Apr-25)
Merging microservices | 21-Apr-2025 | 23-Apr-2025 | 21: Merging microservices (21-Apr-25 - 23-Apr-25)
Manual testing | 23-Apr-2025 | 26-Apr-2025 | 21: Manual testing (23-Apr-25 - 26-Apr-25)
Unit testing | 23-Apr-2025 | 26-Apr-2025 | 21: Unit testing (23-Apr-25 - 26-Apr-25)